# St. John’s University

Mgt. 509 - Operations Management	<insert your name here>

Dr. Patrick Lyons	As of: 8/20/06

# Application of Operations Management

Verbal Outline

# Objective - to reinforce the wide applicability of operations management, especially for students who have careers in accounting, finance, or marketing.

# Topic - Stopwatch Time Study, pages 780–783 of Russell and Chapter 17 outline V.A.

# Situation - Need to develop proper sizing of service delivery to meet client needs. This is an actual situation currently being supported by my organization.

## Position – Delivery Project Executive. Manage IT Service Delivery for a number of large clients. Current annual project and service portfolio in excess of $135 Million.

### Environment:

#### Workstation build/deploy support provided to user population of over 2,500 at 6 locations across the United States.

#### 12 IT Specialists supporting end user community providing both “build/deploy” and “break/fix” workstation support.

### Challenge

#### All 2,500 workstations require a major security upgrade by March 31. Can it be done with the available resources and at what commitment rate?

#### Client has a $160,000 contingency budget. Can this activity be contained within this budget?

# Application

## Construct Appropriate Stopwatch Time Study (See Ch 17 - V.A)

### Divide task into elements

### Time and rate the worker as task is performed

### Compute normal time

#### Normal time =  (performance rating) * (avg actual time)

#### Performance rating - evaluation of individual worker compared to normal worker.

### Compute standard time - allows for unavoidable delays, fatigue, personal time, …
    Standard time = (Normal time) * (1 + Allowance factor)

## See worksheet for details.

# Analysis

## Impact on Human Resources - IT Specialists

### Because of other duties, the IT Specialists should only devote 50% of their time to the upgrade.

### Each of the 12 IT Specialists have, on average, 390 hours of work available until the March 31 deadline.

### Using the above time standard, the 12 IT Specialists will spend 46% of their time on the upgrade. See worksheet for details.

### Thus, staffing constraint is satisfied.

## Improvements in Operations - compared with previous upgrades, there will be:

### Enhanced customer service - end user downtime hours reduced from 125 hours/upgrade to 35 hours/upgrade.

### Reduced errors - because IT Specialists are not rushed, the number of workstations requiring rework is reduced from 215/upgrade to 27/upgrade.

### Transaction costs - because the IT Specialists will spend < 50% of their time on the upgrade, there will be no overtime and the cost ($127,053) will be contained within the budget ($160,000).  See worksheet for details.

# Note - The outline for your case may vary considerably from this one.

## This case is based on one submitted by Mr. Vincent J. Pawlowski.